## Raw_Cross_Section_Data
Cross Section for Re-excavation of Gunapara khal from km. 0.000 to km. 1.750 in Polder no -01 in c/w Tarail-Pachuria Sub-Project under CRISP-WRM under Specialized Division, BWDB, Gopalganj during the year 2024-2025.
[5 empty] | X - Section at km. |  | 0
| Dist | RL |  | M. RL | M. Dist | Area |  | Dist | RL | M. RL | M. Dist | Area
| Pre-work | [6 empty] | Post-work
| 0 | 0.557 | Hugla |  |  |  |  | 0 | 0.557
| 5 | 0.562 |  | 0.5595 | 5 | 2.7975 |  | 5 | 0.562 | 0.5595 | 5 | 2.7975
| 10 | 0.577 | LB | 0.5695 | 5 | 2.8475 |  | 10 | 0.577 | 0.5695 | 5 | 2.8475
| 12 | 0.392 |  | 0.4845 | 2 | 0.969 |  | 12 | 0.392 | 0.4845 | 2 | 0.969
| 14 | 0.296 |  | 0.344 | 2 | 0.688 |  | 14 | 0.296 | 0.344 | 2 | 0.688
| 16 | 0.191 |  | 0.2435 | 2 | 0.487 |  | 16 | 0.191 | 0.2435 | 2 | 0.487
| 18 | 0.096 |  | 0.1435 | 2 | 0.287 |  | 18 | 0.096 | 0.1435 | 2 | 0.287
| 20 | -0.008 | CL | 0.044 | 2 | 0.088 |  | 19.044 | -0.6 | -0.252 | 1.044 | -0.26309
| 22 | 0.093 |  | 0.0425 | 2 | 0.085 |  | 20.544 | -0.6 | -0.6 | 1.5 | -0.9
| 24 | 0.196 |  | 0.1445 | 2 | 0.289 |  | 22.044 | -0.6 | -0.6 | 1.5 | -0.9
| 26 | 0.283 |  | 0.2395 | 2 | 0.479 |  | 23.169 | 0.15 | -0.225 | 1.125 | -0.25312
| 28 | 0.367 |  | 0.325 | 2 | 0.65 |  | 24 | 0.196 | 0.173 | 0.831 | 0.14376
| 30 | 0.707 | RB | 0.537 | 2 | 1.074 |  | 26 | 0.283 | 0.2395 | 2 | 0.479
| 35 | 0.699 |  | 0.703 | 5 | 3.515 |  | 28 | 0.367 | 0.325 | 2 | 0.65
| 40 | 0.694 | Road side | 0.6965 | 5 | 3.4825 |  | 30 | 0.707 | 0.537 | 2 | 1.074
[8 empty] | 35 | 0.699 | 0.703 | 5 | 3.515
[8 empty] | 40 | 0.694 | 0.6965 | 5 | 3.4825
[14 empty] | 0 | 2 |  | 0.75 | -0.5
[11 empty] | 40 | 15.104 |  | 1.5 | 1 |  | 3.25 | -0.5
[14 empty] | 6.5 | 1 |  | 5.75 | -0.5
[14 empty] | 11.5 | 1 |  | 10.8365 | 2.891
[5 empty] | 40 | 17.7385 | Net Area : |  | 17.7385 |  | 15.104 |  | 2.6344 | 13 | 2
Design
[14 empty] | Slope | Width | Depth
[14 empty] | 1.00 : 1.50 | 3 | -0.6
[5 empty] | X - Section at km. |  | 0.1
| Pre-work | [5 empty] | . | Post-work
| 0 | 2.676 | Home stead
| 5 | 2.671 |  | 2.6735 | 5 | 13.3675 |  | 0 | 2.676
| 10 | 2.7 | LB | 2.6855 | 5 | 13.4275 |  | 5 | 2.671 | 2.6735 | 5 | 13.3675
| 11 | 1.691 |  | 2.1955 | 1 | 2.1955 |  | 8.5 | 2.7 | 2.6855 | 3.5 | 9.3993
| 12 | 1.027 |  | 1.359 | 1 | 1.359 |  | 13.45 | -0.6 | 1.05 | 4.95 | 5.1975
| 13 | 0.634 |  | 0.8305 | 1 | 0.8305 |  | 14.95 | -0.6 | -0.6 | 1.5 | -0.9
| 14.5 | 0.533 | CL | 0.5835 | 1.5 | 0.87525 |  | 16.45 | -0.6 | -0.6 | 1.5 | -0.9
| 16 | 0.636 |  | 0.5845 | 1.5 | 0.87675 |  | 21.6865 | 2.891 | 1.1455 | 5.2365 | 5.9984
| 17 | 1.03 |  | 0.833 | 1 | 0.833 |  | 25 | 2.896 | 2.8935 | 3.3135 | 9.5876
| 18 | 1.585 |  | 1.3075 | 1 | 1.3075 |  | 30 | 2.883 | 2.8895 | 5 | 14.4475
| 19 | 2.353 | RB | 1.969 | 1 | 1.969
| 20 | 2.365 |  | 2.359 | 1 | 2.359
| 21 | 2.896 |  | 2.6305 | 1 | 2.6305
| 25 | 2.891 |  | 2.8935 | 4 | 11.574
| 30 | 2.883 | Garden | 2.887 | 5 | 14.435
[14 empty] | -1.5 | 1
[14 empty] | 3.5 | 1
[14 empty] | 8.5 | 1
[14 empty] | 10 | 2
[5 empty] | 30 | 68.04 | [5 empty] | 56.1978
[7 empty] | Net Area : |  | 68.04 | - | 56.1978 | 11.8422
[5 empty] | X - Section at km. |  | 0.2 | [7 empty] | 3
| Pre-work | [5 empty] | . | Post-work
| 0 | 1.421 | Paddy land
| 5 | 1.432 |  | 1.4265 | 5 | 7.1325
| 6 | 2.717 |  | 2.0745 | 1 | 2.0745
| 8 | 2.706 |  | 2.7115 | 2 | 5.423
| 9 | 2.108 |  | 2.407 | 1 | 2.407
| 10 | 2.101 | LB | 2.1045 | 1 | 2.1045
| 11 | 1.326 |  | 1.7135 | 1 | 1.7135 |  | 5 | 1.432
| 12 | 0.905 |  | 1.1155 | 1 | 1.1155 |  | 6 | 2.717 | 2.0745 | 1 | 2.0745
| 13 | 0.621 |  | 0.763 | 1 | 0.763 |  | 7.5 | 2.706 | 2.7115 | 1.5 | 4.0672
| 14.5 | 0.518 | CL | 0.5695 | 1.5 | 0.85425 |  | 12.459 | -0.6 | 1.053 | 4.959 | 5.2218
| 16 | 0.619 |  | 0.5685 | 1.5 | 0.85275 |  | 13.959 | -0.6 | -0.6 | 1.5 | -0.9
| 17 | 0.93 |  | 0.7745 | 1 | 0.7745 |  | 15.459 | -0.6 | -0.6 | 1.5 | -0.9
| 18 | 1.306 |  | 1.118 | 1 | 1.118 |  | 20.274 | 2.61 | 1.005 | 4.815 | 4.8391
| 19 | 2.612 | RB | 1.959 | 1 | 1.959 |  | 22 | 2.618 | 2.614 | 1.726 | 4.5118
| 22 | 2.618 |  | 2.615 | 3 | 7.845 |  | 24 | 1.431 | 2.0245 | 2 | 4.049
| 24 | 1.431 |  | 2.0245 | 2 | 4.049 |  | 25 | 1.235 | 1.333 | 1 | 1.333
| 25 | 1.235 | Pond | 1.333 | 1 | 1.333
[5 empty] | 25 | 41.519 | [5 empty] | 24.2964
[7 empty] | Net Area : |  | 41.519 | - | 24.2964 | 17.2226 | 100 |  | 1722.2584
[5 empty] | X - Section at km. |  | 0.3 | [7 empty] | 3
| Pre-work | [5 empty] | . | Post-work
| 0 | 2.583 | Open land
| 5 | 2.569 |  | 2.576 | 5 | 12.88
| 10 | 2.561 | LB | 2.565 | 5 | 12.825
| 11 | 1.596 |  | 2.0785 | 1 | 2.0785
| 12 | 1.002 |  | 1.299 | 1 | 1.299
| 13 | 0.488 |  | 0.745 | 1 | 0.745
| 14 | 0.487 | CL | 0.4875 | 1 | 0.4875 |  | 0 | 2.583
| 15 | 0.492 |  | 0.4895 | 1 | 0.4895 |  | 5 | 2.569 | 2.576 | 5 | 12.88
| 16 | 0.991 |  | 0.7415 | 1 | 0.7415 |  | 8 | 2.561 | 2.565 | 3 | 7.695
| 17 | 1.639 |  | 1.315 | 1 | 1.315 |  | 12.7415 | -0.6 | 0.9805 | 4.7415 | 4.649
| 18 | 2.493 | RB | 2.066 | 1 | 2.066 |  | 14.2415 | -0.6 | -0.6 | 1.5 | -0.9
| 23 | 2.505 |  | 2.499 | 5 | 12.495 |  | 15.7415 | -0.6 | -0.6 | 1.5 | -0.9
| 28 | 2.519 | Open land | 2.512 | 5 | 12.56 |  | 20.399 | 2.505 | 0.9525 | 4.6575 | 4.4363
[8 empty] | 23 | 2.505 | 2.505 | 2.601 | 6.5155
[8 empty] | 28 | 2.519 | 2.512 | 5 | 12.56
[11 empty] | 28 | 46.9358
[5 empty] | 28 | 59.982
[7 empty] | Net Area : |  | 59.982 | - | 46.9358 | 13.0462
[5 empty] | X - Section at km. |  | 0.355
| Pre-work | [5 empty] | . | Post-work | [6 empty] | 0
| 0 | 1.413 | Paddy land |  |  |  |  | 0 | 1.413
| 5 | 1.408 |  | 1.4105 | 5 | 7.0525 |  | 5 | 1.408 | 1.4105 | 5 | 7.0525
| 10 | 1.402 | LB | 1.405 | 5 | 7.025 |  | 10 | 1.402 | 1.405 | 5 | 7.025
| 11 | 1.207 |  | 1.3045 | 1 | 1.3045 |  | 13.003 | -0.6 | 0.401 | 3.003 | 1.2042
| 12 | 1.002 |  | 1.1045 | 1 | 1.1045 |  | 14.503 | -0.6 | -0.6 | 1.5 | -0.9
| 13 | 0.838 |  | 0.92 | 1 | 0.92 |  | 16.003 | -0.6 | -0.6 | 1.5 | -0.9
| 15 | 0.738 | CL | 0.788 | 2 | 1.576 |  | 20.5 | 2.398 | 0.899 | 4.497 | 4.0428
| 17 | 0.84 |  | 0.789 | 2 | 1.578 |  | 25 | 2.398 | 2.398 | 4.5 | 10.791
| 18 | 1.13 |  | 0.985 | 1 | 0.985 |  | 30 | 2.403 | 2.4005 | 5 | 12.0025
| 19 | 1.413 |  | 1.2715 | 1 | 1.2715
| 20 | 2.387 | RB | 1.9 | 1 | 1.9
| 25 | 2.398 |  | 2.3925 | 5 | 11.9625
| 30 | 2.403 | Paddy land | 2.4005 | 5 | 12.0025
[14 empty] | 0.75 | -0.5
[14 empty] | 3.25 | -0.5
[14 empty] | 5.75 | -0.5
[14 empty] | 10.415 | 2.61
[11 empty] | 30 | 40.318
[5 empty] | 30 | 48.682
[7 empty] | Net Area : |  | 48.682 | - | 40.318 | 8.364
[5 empty] | X - Section at km. |  | 0.36
| Pre-work | [5 empty] | . | Post-work | [6 empty] | 7.5705
| 0 | 2.371 | Paddy land
| 5 | 2.359 |  | 2.365 | 5 | 11.825
| 10 | 2.353 | LB | 2.356 | 5 | 11.78
| 11 | 1.34 |  | 1.8465 | 1 | 1.8465
| 12 | 1.334 |  | 1.337 | 1 | 1.337 |  | 0 | 2.371
| 13 | 1.323 |  | 1.3285 | 1 | 1.3285 |  | 5 | 2.359 | 2.365 | 5 | 11.825
| 14 | 1.278 | CL | 1.3005 | 1 | 1.3005 |  | 8 | 2.353 | 2.356 | 3 | 7.068
| 15 | 1.319 |  | 1.2985 | 1 | 1.2985 |  | 12.4295 | -0.6 | 0.8765 | 4.4295 | 3.8825
| 16 | 1.324 |  | 1.3215 | 1 | 1.3215 |  | 13.9295 | -0.6 | -0.6 | 1.5 | -0.9
| 17 | 1.33 |  | 1.327 | 1 | 1.327 |  | 15.4295 | -0.6 | -0.6 | 1.5 | -0.9
| 18 | 2.153 | RB | 1.7415 | 1 | 1.7415 |  | 19.559 | 2.153 | 0.7765 | 4.1295 | 3.2066
| 23 | 2.159 |  | 2.156 | 5 | 10.78 |  | 23 | 2.159 | 2.156 | 3.441 | 7.4188
| 28 | 2.172 | Paddy land | 2.1655 | 5 | 10.8275 |  | 28 | 2.172 | 2.1655 | 5 | 10.8275
[14 empty] | 0.75 | -0.5
[14 empty] | 3.25 | -0.5
[14 empty] | 5.75 | -0.5
[14 empty] | 10.415 | 2.61
[11 empty] | 28 | 42.4283
[5 empty] | 28 | 56.7135
[7 empty] | Net Area : |  | 56.7135 | - | 42.4283 | 14.2852
[5 empty] | X - Section at km. |  | 0.4
| Pre-work | [5 empty] | . | Post-work | [6 empty] | 0
| 0 | 1.858 | House Area |  |  |  |  | 0 | 1.858
| 5 | 1.853 |  | 1.8555 | 5 | 9.2775 |  | 5 | 1.853 | 1.8555 | 5 | 9.2775
| 10 | 1.847 | LB | 1.85 | 5 | 9.25 |  | 10 | 1.847 | 1.85 | 5 | 9.25
| 11 | 1.754 |  | 1.8005 | 1 | 1.8005 |  | 13.6705 | -0.6 | 0.6235 | 3.6705 | 2.2886
| 12 | 1.607 |  | 1.6805 | 1 | 1.6805 |  | 15.1705 | -0.6 | -0.6 | 1.5 | -0.9
| 13 | 1.487 |  | 1.547 | 1 | 1.547 |  | 16.6705 | -0.6 | -0.6 | 1.5 | -0.9
| 15 | 1.483 | CL | 1.485 | 2 | 2.97 |  | 20.608 | 2.025 | 0.7125 | 3.9375 | 2.8055
| 17 | 1.485 |  | 1.484 | 2 | 2.968 |  | 25 | 2.025 | 2.025 | 4.392 | 8.8938
| 18 | 1.594 |  | 1.5395 | 1 | 1.5395 |  | 30 | 2.016 | 2.0205 | 5 | 10.1025
| 19 | 1.749 |  | 1.6715 | 1 | 1.6715
| 20 | 2.034 | RB | 1.8915 | 1 | 1.8915
| 25 | 2.025 |  | 2.0295 | 5 | 10.1475
| 30 | 2.016 | Paddy land | 2.0205 | 5 | 10.1025
[11 empty] | 30 | 31.5403
[5 empty] | 30 | 54.846
[7 empty] | Net Area : |  | 54.846 | - | 31.5403 | 23.3057
[5 empty] | X - Section at km. |  | 0.5
| Pre-work | [5 empty] | . | Post-work | [6 empty] | 3
| 0 | 1.566 | Paddy land
| 5 | 1.561 |  | 1.5635 | 5 | 7.8175
| 10 | 1.55 | LB | 1.5555 | 5 | 7.7775
| 11 | 1.523 |  | 1.5365 | 1 | 1.5365
| 12 | 1.506 |  | 1.5145 | 1 | 1.5145
| 13 | 1.483 |  | 1.4945 | 1 | 1.4945
| 15 | 1.437 | CL | 1.46 | 2 | 2.92 |  | 0 | 1.566
| 17 | 1.486 |  | 1.4615 | 2 | 2.923 |  | 5 | 1.561 | 1.5635 | 5 | 7.8175
| 18 | 1.58 |  | 1.533 | 1 | 1.533 |  | 10 | 1.55 | 1.5555 | 5 | 7.7775
| 19 | 1.675 |  | 1.6275 | 1 | 1.6275 |  | 13.225 | -0.6 | 0.475 | 3.225 | 1.5319
| 20 | 1.868 | RB | 1.7715 | 1 | 1.7715 |  | 14.725 | -0.6 | -0.6 | 1.5 | -0.9
| 25 | 1.874 |  | 1.871 | 5 | 9.355 |  | 16.225 | -0.6 | -0.6 | 1.5 | -0.9
| 30 | 1.889 | Paddy land | 1.8815 | 5 | 9.4075 |  | 19.75 | 1.75 | 0.575 | 3.525 | 2.0269
[8 empty] | 20 | 1.868 | 1.809 | 0.25 | 0.45225
[8 empty] | 25 | 1.874 | 1.871 | 5 | 9.355
[8 empty] | 30 | 1.889 | 1.8815 | 5 | 9.4075
[11 empty] | 30 | 36.5685
[5 empty] | 30 | 49.678
[7 empty] | Net Area : |  | 49.678 | - | 36.5685 | 13.1095
[5 empty] | X - Section at km. |  | 0.575
| Pre-work | [5 empty] | . | Post-work | [6 empty] | 5.5675
| 0 | 1.609 | Paddy land
| 5 | 1.604 |  | 1.6065 | 5 | 8.0325
| 8 | 1.598 |  | 1.601 | 3 | 4.803
| 9 | 2.445 |  | 2.0215 | 1 | 2.0215
| 10 | 2.434 | LB | 2.4395 | 1 | 2.4395
| 11 | 1.859 |  | 2.1465 | 1 | 2.1465
| 12 | 1.569 |  | 1.714 | 1 | 1.714
| 13 | 1.476 |  | 1.5225 | 1 | 1.5225 |  | 0 | 1.609
| 15 | 1.37 | CL | 1.423 | 2 | 2.846 |  | 5 | 1.604 | 1.6065 | 5 | 8.0325
| 17 | 1.473 |  | 1.4215 | 2 | 2.843 |  | 8 | 1.598 | 1.601 | 3 | 4.803
| 18 | 1.577 |  | 1.525 | 1 | 1.525 |  | 9 | 2.445 | 2.0215 | 1 | 2.0215
| 19 | 1.843 |  | 1.71 | 1 | 1.71 |  | 13.5675 | -0.6 | 0.9225 | 4.5675 | 4.2135
| 20 | 2.317 | RB | 2.08 | 1 | 2.08 |  | 15.0675 | -0.6 | -0.6 | 1.5 | -0.9
| 25 | 2.325 |  | 2.321 | 5 | 11.605 |  | 16.5675 | -0.6 | -0.6 | 1.5 | -0.9
| 30 | 2.334 | Home stead | 2.3295 | 5 | 11.6475 |  | 20.955 | 2.325 | 0.8625 | 4.3875 | 3.7842
[8 empty] | 25 | 2.325 | 2.325 | 4.045 | 9.4046
[8 empty] | 30 | 2.334 | 2.3295 | 5 | 11.6475
[11 empty] | 30 | 42.1069
[5 empty] | 30 | 56.936
[7 empty] | Net Area : |  | 56.936 | - | 42.1069 | 14.8291
[5 empty] | X - Section at km. |  | 0.58
| Pre-work | [5 empty] | . | Post-work | [6 empty] | 6.0225
| 0 | 1.636 | Paddy land
| 5 | 1.629 |  | 1.6325 | 5 | 8.1625
| 8 | 1.624 |  | 1.6265 | 3 | 4.8795
| 9 | 2.415 |  | 2.0195 | 1 | 2.0195
| 10 | 2.406 | LB | 2.4105 | 1 | 2.4105
| 11 | 1.858 |  | 2.132 | 1 | 2.132
| 12 | 1.446 |  | 1.652 | 1 | 1.652 |  | 0 | 1.636
| 13 | 1.16 |  | 1.303 | 1 | 1.303 |  | 5 | 1.629 | 1.6325 | 5 | 8.1625
| 14.5 | 1.058 | CL | 1.109 | 1.5 | 1.6635 |  | 8 | 1.624 | 1.6265 | 3 | 4.8795
| 16 | 1.159 |  | 1.1085 | 1.5 | 1.6627 |  | 9 | 2.415 | 2.0195 | 1 | 2.0195
| 17 | 1.433 |  | 1.296 | 1 | 1.296 |  | 13.5225 | -0.6 | 0.9075 | 4.5225 | 4.1042
| 18 | 1.769 |  | 1.601 | 1 | 1.601 |  | 15.0225 | -0.6 | -0.6 | 1.5 | -0.9
| 19 | 2.276 | RB | 2.0225 | 1 | 2.0225 |  | 16.5225 | -0.6 | -0.6 | 1.5 | -0.9
| 25 | 2.283 |  | 2.2795 | 6 | 13.677 |  | 20.847 | 2.283 | 0.8415 | 4.3245 | 3.6391
| 30 | 2.29 | Home stead | 2.2865 | 5 | 11.4325 |  | 25 | 2.283 | 2.283 | 4.153 | 9.4813
[8 empty] | 30 | 2.29 | 2.2865 | 5 | 11.4325
[11 empty] | 30 | 41.9185
[5 empty] | 30 | 55.9142
[7 empty] | Net Area : |  | 55.9142 | - | 41.9185 | 13.9957
[5 empty] | X - Section at km. |  | 0.6
| Pre-work | [5 empty] | . | Post-work | [6 empty] | 6.1735
| 0 | 1.719 | Garden
| 5 | 1.714 |  | 1.7165 | 5 | 8.5825
| 7 | 1.706 |  | 1.71 | 2 | 3.42
| 8 | 2.46 |  | 2.083 | 1 | 2.083
| 10 | 2.449 | LB | 2.4545 | 2 | 4.909
| 11 | 1.766 |  | 2.1075 | 1 | 2.1075
| 12 | 1.369 |  | 1.5675 | 1 | 1.5675 |  | 0 | 1.719
| 14 | 1.114 |  | 1.2415 | 2 | 2.483 |  | 5 | 1.714 | 1.7165 | 5 | 8.5825
| 15.5 | 1.013 | CL | 1.0635 | 1.5 | 1.5952 |  | 7 | 1.706 | 1.71 | 2 | 3.42
| 17 | 1.115 |  | 1.064 | 1.5 | 1.596 |  | 8 | 2.46 | 2.083 | 1 | 2.083
| 19 | 1.35 |  | 1.2325 | 2 | 2.465 |  | 9.6 | 2.449 | 2.4545 | 1.6 | 3.9272
| 20 | 1.745 |  | 1.5475 | 1 | 1.5475 |  | 14.1735 | -0.6 | 0.9245 | 4.5735 | 4.2282
| 21 | 2.215 | RB | 1.98 | 1 | 1.98 |  | 15.6735 | -0.6 | -0.6 | 1.5 | -0.9
| 25 | 2.229 |  | 2.222 | 4 | 8.888 |  | 17.1735 | -0.6 | -0.6 | 1.5 | -0.9
| 30 | 2.234 | Garden | 2.2315 | 5 | 11.1575 |  | 21.396 | 2.215 | 0.8075 | 4.2225 | 3.4097
[8 empty] | 25 | 2.229 | 2.222 | 3.604 | 8.0081
[8 empty] | 30 | 2.234 | 2.2315 | 5 | 11.1575
[5 empty] | 30 | 54.3817 |  |  |  |  | 30 | 43.0162
[7 empty] | Net Area : |  | 54.3817 | - | 43.0162 | 11.3656
[5 empty] | X - Section at km. |  | 0.7
| Pre-work | [5 empty] | . | Post-work | [6 empty] | 3
| 0 | 1.415 | Open land
| 5 | 1.426 |  | 1.4205 | 5 | 7.1025
| 7 | 1.435 |  | 1.4305 | 2 | 2.861
| 8 | 2.351 |  | 1.893 | 1 | 1.893
| 10 | 2.346 | LB | 2.3485 | 2 | 4.697
| 11 | 1.36 |  | 1.853 | 1 | 1.853
| 13 | 0.762 |  | 1.061 | 2 | 2.122
| 15 | 0.331 |  | 0.5465 | 2 | 1.093 |  | 0 | 1.415
| 16 | 0.228 | CL | 0.2795 | 1 | 0.2795 |  | 5 | 1.426 | 1.4205 | 5 | 7.1025
| 17 | 0.33 |  | 0.279 | 1 | 0.279 |  | 7 | 1.435 | 1.4305 | 2 | 2.861
| 19 | 0.745 |  | 0.5375 | 2 | 1.075 |  | 8 | 2.351 | 1.893 | 1 | 1.893
| 21 | 1.302 |  | 1.0235 | 2 | 2.047 |  | 10 | 2.346 | 2.3485 | 2 | 4.697
| 22 | 2.075 | RB | 1.6885 | 1 | 1.6885 |  | 11 | 1.36 | 1.853 | 1 | 1.853
| 27 | 2.085 |  | 2.08 | 5 | 10.4 |  | 13.94 | -0.6 | 0.38 | 2.94 | 1.1172
| 32 | 2.09 | Garden | 2.0875 | 5 | 10.4375 |  | 15.44 | -0.6 | -0.6 | 1.5 | -0.9
[8 empty] | 16.94 | -0.6 | -0.6 | 1.5 | -0.9
[8 empty] | 18.815 | 0.65 | 0.025 | 1.875 | 0.046875
[8 empty] | 19 | 0.745 | 0.6975 | 0.185 | 0.12904 |  |  | 0.75 | -0.5
[8 empty] | 21 | 1.302 | 1.0235 | 2 | 2.047 |  |  | 3.25 | -0.5
[8 empty] | 22 | 2.075 | 1.6885 | 1 | 1.6885 |  |  | 5.75 | -0.5
[8 empty] | 27 | 2.085 | 2.08 | 5 | 10.4 |  |  | 10.415 | 2.61
[8 empty] | 32 | 2.09 | 2.0875 | 5 | 10.4375
[5 empty] | 32 | 47.828 |  |  |  |  | 32 | 42.4726
[7 empty] | Net Area : |  | 47.828 | - | 42.4726 | 5.3554
[5 empty] | X - Section at km. |  | 0.8
| Pre-work | [5 empty] | . | Post-work | [6 empty] | 6.2325
| 0 | 1.64 | Paddy land
| 7 | 1.652 |  | 1.646 | 7 | 11.522
| 8 | 2.555 |  | 2.1035 | 1 | 2.1035
| 10 | 2.537 | LB | 2.546 | 2 | 5.092
| 11 | 1.34 |  | 1.9385 | 1 | 1.9385
| 12 | 0.555 |  | 0.9475 | 1 | 0.9475
| 13.5 | 0.451 | CL | 0.503 | 1.5 | 0.7545
| 15 | 0.552 |  | 0.5015 | 1.5 | 0.75225 |  | 0 | 1.64
| 16 | 1.297 |  | 0.9245 | 1 | 0.9245 |  | 7 | 1.652 | 1.646 | 7 | 11.522
| 17 | 3.0489 | RB | 2.173 | 1 | 2.173 |  | 8 | 2.555 | 2.1035 | 1 | 2.1035
| 20 | 3.057 |  | 3.053 | 3 | 9.1589 |  | 12.7325 | -0.6 | 0.9775 | 4.7325 | 4.626
| 22 | 1.94 |  | 2.4985 | 2 | 4.997 |  | 14.2325 | -0.6 | -0.6 | 1.5 | -0.9
| 24 | 0.947 | Pond | 1.4435 | 2 | 2.887 |  | 15.7325 | -0.6 | -0.6 | 1.5 | -0.9
[8 empty] | 20.6825 | 2.7 | 1.05 | 4.95 | 5.1975
[8 empty] | 22 | 1.94 | 2.32 | 1.3175 | 3.0566
[8 empty] | 24 | 0.947 | 1.4435 | 2 | 2.887
[5 empty] | 24 | 43.2506 |  |  |  |  | 24 | 27.5926
[7 empty] | Net Area : |  | 43.2506 | - | 27.5926 | 15.6579
[5 empty] | X - Section at km. |  | 0.9
| Pre-work | [5 empty] | . | Post-work | [6 empty] | 5.7855
| 0 | 2.271 | Home stead
| 5 | 2.266 |  | 2.2685 | 5 | 11.3425
| 10 | 2.257 | LB | 2.2615 | 5 | 11.3075
| 11 | 1.411 |  | 1.834 | 1 | 1.834
| 12 | 0.992 |  | 1.2015 | 1 | 1.2015
| 13 | 0.704 |  | 0.848 | 1 | 0.848
| 15 | 0.6056 | CL | 0.6548 | 2 | 1.3096
| 17 | 0.706 |  | 0.6558 | 2 | 1.3116 |  | 0 | 2.271
| 18 | 1.013 |  | 0.8595 | 1 | 0.8595 |  | 5 | 2.266 | 2.2685 | 5 | 11.3425
| 19 | 1.391 |  | 1.202 | 1 | 1.202 |  | 9.25 | 2.257 | 2.2615 | 4.25 | 9.6114
| 20 | 2.45 | RB | 1.9205 | 1 | 1.9205 |  | 13.5355 | -0.6 | 0.8285 | 4.2855 | 3.5505
| 23 | 2.461 | Mondir | 2.4555 | 3 | 7.3665 |  | 15.0355 | -0.6 | -0.6 | 1.5 | -0.9
[8 empty] | 16.5355 | -0.6 | -0.6 | 1.5 | -0.9
[8 empty] | 21.1105 | 2.45 | 0.925 | 4.575 | 4.2319
[8 empty] | 23 | 2.461 | 2.4555 | 1.8895 | 4.6397
[14 empty] | 0.75 | -0.5
[14 empty] | 3.25 | -0.5
[14 empty] | 5.75 | -0.5
[14 empty] | 10.415 | 2.61
[5 empty] | 23 | 40.5032 |  |  |  |  | 23 | 31.576
[7 empty] | Net Area : |  | 40.5032 | - | 31.576 | 8.9272
[5 empty] | X - Section at km. |  | 1
| Pre-work | [5 empty] | . | Post-work | [6 empty] | 3
| 0 | 2.328 | House
| 4 | 2.323 | LB | 2.3255 | 4 | 9.302
| 5 | 1.702 |  | 2.0125 | 1 | 2.0125
| 6 | 1.398 |  | 1.55 | 1 | 1.55
| 7 | 1.177 |  | 1.2875 | 1 | 1.2875
| 8.5 | 1.073 | CL | 1.125 | 1.5 | 1.6875
| 10 | 1.175 |  | 1.124 | 1.5 | 1.686
| 11 | 1.402 |  | 1.2885 | 1 | 1.2885 |  | 0 | 2.328
| 12 | 1.805 |  | 1.6035 | 1 | 1.6035 |  | 2.5 | 2.323 | 2.3255 | 2.5 | 5.8137
| 13 | 2.688 | RB | 2.2465 | 1 | 2.2465 |  | 6.8845 | -0.6 | 0.8615 | 4.3845 | 3.7772
| 16 | 2.693 | House | 2.6905 | 3 | 8.0715 |  | 8.3845 | -0.6 | -0.6 | 1.5 | -0.9
[8 empty] | 9.8845 | -0.6 | -0.6 | 1.5 | -0.9
[8 empty] | 14.824 | 2.693 | 1.0465 | 4.9395 | 5.1692
[8 empty] | 16 | 2.693 | 2.693 | 1.176 | 3.167
[5 empty] | 16 | 30.7355 |  |  |  |  | 16 | 16.1272
[7 empty] | Net Area : |  | 30.7355 | - | 16.1272 | 14.6083
[5 empty] | X - Section at km. |  | 1.028
| Pre-work | [5 empty] | . | Post-work | [6 empty] | 0
| 0 | 3.328 | House
| 2 | 3.323 | LB | 3.3255 | 2 | 6.651 |  | 0 | 3.328
| 3 | 1.985 |  | 2.654 | 1 | 2.654 |  | 5.892 | -0.6 | 1.364 | 5.892 | 8.0367
| 4 | 1.173 |  | 1.579 | 1 | 1.579 |  | 7.392 | -0.6 | -0.6 | 1.5 | -0.9
| 5 | 0.799 |  | 0.986 | 1 | 0.986 |  | 8.892 | -0.6 | -0.6 | 1.5 | -0.9
| 6.5 | 0.697 | CL | 0.748 | 1.5 | 1.122 |  | 12.744 | 1.968 | 0.684 | 3.852 | 2.6348
| 8 | 0.798 |  | 0.7475 | 1.5 | 1.1213 |  | 15 | 1.968 | 1.968 | 2.256 | 4.4398
| 9 | 1.105 |  | 0.9515 | 1 | 0.9515
| 10 | 1.439 |  | 1.272 | 1 | 1.272
| 11 | 1.975 | RB | 1.707 | 1 | 1.707
| 12 | 1.968 | Shop | 1.9715 | 1 | 1.9715
| 15 | 1.968 |  | 1.968 | 3 | 5.904
[5 empty] | 15 | 25.9192 |  |  |  |  | 15 | 13.3113
[7 empty] | Net Area : |  | 25.9192 | - | 13.3113 | 12.608
[5 empty] | X - Section at km. |  | 1.043
| Pre-work | [5 empty] | . | Post-work | [6 empty] | -16
| 0 | 1.904 | Shop
| 3 | 1.895 | LB | 1.8995 | 3 | 5.6985
| 4 | 1.399 |  | 1.647 | 1 | 1.647
| 6 | 1.109 |  | 1.254 | 2 | 2.508
| 8 | 0.861 |  | 0.985 | 2 | 1.97
| 9 | 0.788 | CL | 0.8245 | 1 | 0.8245 |  | 0 | 1.904
| 10 | 0.86 |  | 0.824 | 1 | 0.824 |  | 3 | 1.895 | 1.8995 | 3 | 5.6985
| 12 | 1.205 |  | 1.0325 | 2 | 2.065 |  | 4 | 1.399 | 1.647 | 1 | 1.647
| 14 | 1.872 |  | 1.5385 | 2 | 3.077 |  | 6.9985 | -0.6 | 0.3995 | 2.9985 | 1.1979
| 15 | 3.483 | RB | 2.6775 | 1 | 2.6775 |  | 8.4985 | -0.6 | -0.6 | 1.5 | -0.9
| 16 | 3.497 | Shop | 3.49 | 1 | 3.49 |  | 9.9985 | -0.6 | -0.6 | 1.5 | -0.9
| 16.59 | 3.497 |  | 3.497 | 0.59 | 2.0632 |  | 16.144 | 3.497 | 1.4485 | 6.1455 | 8.9018
[8 empty] | 16 | 3.497 | 3.497 | -0.144 | -0.50357
[8 empty] | 16.59 | 3.497 | 3.497 | 0.59 | 2.0632
[14 empty] | 0.75 | -0.5
[14 empty] | 3.25 | -0.5
[14 empty] | 5.75 | -0.5
[14 empty] | 9.452 | 1.968
[5 empty] | 16.59 | 26.8447 |  |  |  |  | 16.59 | 17.2048
[7 empty] | Net Area : |  | 26.8447 | - | 17.2048 | 9.6399
[5 empty] | X - Section at km. |  | 1.1
| Pre-work | [5 empty] | . | Post-work | [6 empty] | 0
| 0 | 1.455 | Paddy land
| 5 | 1.464 |  | 1.4595 | 5 | 7.2975
| 10 | 1.469 | LB | 1.4665 | 5 | 7.3325
| 11 | 0.759 |  | 1.114 | 1 | 1.114 |  | 0 | 1.455
| 12 | 0.464 |  | 0.6115 | 1 | 0.6115 |  | 5 | 1.464 | 1.4595 | 5 | 7.2975
| 13 | 0.167 |  | 0.3155 | 1 | 0.3155 |  | 8.5 | 1.469 | 1.4665 | 3.5 | 5.1327
| 14 | 0.065 | CL | 0.116 | 1 | 0.116 |  | 11.6035 | -0.6 | 0.4345 | 3.1035 | 1.3485
| 15 | 0.169 |  | 0.117 | 1 | 0.117 |  | 13.1035 | -0.6 | -0.6 | 1.5 | -0.9
| 16 | 0.558 |  | 0.3635 | 1 | 0.3635 |  | 14.6035 | -0.6 | -0.6 | 1.5 | -0.9
| 17 | 1.56 |  | 1.059 | 1 | 1.059 |  | 19.4905 | 2.658 | 1.029 | 4.887 | 5.0287
| 18 | 2.646 | RB | 2.103 | 1 | 2.103 |  | 20.19 | 2.658 | 2.658 | 0.6995 | 1.8593
| 19 | 2.658 | House | 2.652 | 1 | 2.652
| 20.19 | 2.658 |  | 2.658 | 1.19 | 3.163
[5 empty] | 20.19 | 26.2445 |  |  |  |  | 20.19 | 18.8667
[7 empty] | Net Area : |  | 26.2445 | - | 18.8667 | 7.3778
[5 empty] | X - Section at km. |  | 1.2
| Pre-work | [5 empty] | . | Post-work | [6 empty] | -28
| 0 | 0.719 | Low land
| 5 | 0.714 |  | 0.7165 | 5 | 3.5825
| 10 | 0.706 | LB | 0.71 | 5 | 3.55
| 11 | 0.439 |  | 0.5725 | 1 | 0.5725
| 12 | 0.324 |  | 0.3815 | 1 | 0.3815 |  | 0 | 0.719
| 13 | 0.236 |  | 0.28 | 1 | 0.28 |  | 5 | 0.714 | 0.7165 | 5 | 3.5825
| 14 | 0.137 | CL | 0.1865 | 1 | 0.1865 |  | 10 | 0.706 | 0.71 | 5 | 3.55
| 15 | 0.239 |  | 0.188 | 1 | 0.188 |  | 11.959 | -0.6 | 0.053 | 1.959 | 0.10383
| 16 | 0.536 |  | 0.3875 | 1 | 0.3875 |  | 13.459 | -0.6 | -0.6 | 1.5 | -0.9
| 17 | 1.035 |  | 0.7855 | 1 | 0.7855 |  | 14.959 | -0.6 | -0.6 | 1.5 | -0.9
| 18 | 1.974 | RB | 1.5045 | 1 | 1.5045 |  | 18.814 | 1.97 | 0.685 | 3.855 | 2.6407
| 23 | 1.979 |  | 1.9765 | 5 | 9.8825 |  | 23 | 1.979 | 1.9745 | 4.186 | 8.2653
| 28 | 1.986 | Home stead | 1.9825 | 5 | 9.9125 |  | 28 | 1.986 | 1.9825 | 5 | 9.9125
[5 empty] | 28 | 31.2135 |  |  |  |  | 28 | 26.2548
[7 empty] | Net Area : |  | 31.2135 | - | 26.2548 | 4.9587
[5 empty] | X - Section at km. |  | 1.3
| Pre-work | [5 empty] | . | Post-work | [6 empty] | 3.2135
| 0 | 2.111 | Garden
| 5 | 2.097 |  | 2.104 | 5 | 10.52
| 10 | 2.086 | LB | 2.0915 | 5 | 10.4575
| 11 | 1.127 |  | 1.6065 | 1 | 1.6065
| 13 | 0.591 |  | 0.859 | 2 | 1.718
| 15 | 0.072 |  | 0.3315 | 2 | 0.663 |  | 0 | 2.111
| 16 | -0.029 | CL | 0.0215 | 1 | 0.0215 |  | 5 | 2.097 | 2.104 | 5 | 10.52
| 17 | 0.076 |  | 0.0235 | 1 | 0.0235 |  | 10 | 2.086 | 2.0915 | 5 | 10.4575
| 19 | 0.52 |  | 0.298 | 2 | 0.596 |  | 11 | 1.127 | 1.6065 | 1 | 1.6065
| 21 | 1.123 |  | 0.8215 | 2 | 1.643 |  | 13 | 0.591 | 0.859 | 2 | 1.718
| 22 | 2.201 | RB | 1.662 | 1 | 1.662 |  | 14.7865 | -0.6 | -0.0045 | 1.7865 | -0.0080393
| 27 | 2.206 |  | 2.2035 | 5 | 11.0175 |  | 16.2865 | -0.6 | -0.6 | 1.5 | -0.9
| 32 | 2.222 | House Area | 2.214 | 5 | 11.07 |  | 17.7865 | -0.6 | -0.6 | 1.5 | -0.9
[8 empty] | 19.7365 | 0.7 | 0.05 | 1.95 | 0.0975
[8 empty] | 21 | 1.123 | 0.9115 | 1.2635 | 1.1517
[8 empty] | 22 | 2.201 | 1.662 | 1 | 1.662
[8 empty] | 27 | 2.206 | 2.2035 | 5 | 11.0175
[8 empty] | 32 | 2.222 | 2.214 | 5 | 11.07
[5 empty] | 32 | 50.9985 |  |  |  |  | 32 | 47.4926
[7 empty] | Net Area : |  | 50.9985 | - | 47.4926 | 3.5059
[5 empty] | X - Section at km. |  | 1.4
| Pre-work | [5 empty] | . | Post-work | [6 empty] | 2.9015
| 0 | 1.944 | House
| 4 | 1.937 | LB | 1.9405 | 4 | 7.762
| 5 | 0.941 |  | 1.439 | 1 | 1.439
| 7 | 0.343 |  | 0.642 | 2 | 1.284
| 9 | -0.001 |  | 0.171 | 2 | 0.342 |  | 0 | 1.944
| 11 | -0.103 | CL | -0.052 | 2 | -0.104 |  | 4 | 1.937 | 1.9405 | 4 | 7.762
| 13 | -0.002 |  | -0.0525 | 2 | -0.105 |  | 5 | 0.941 | 1.439 | 1 | 1.439
| 15 | 0.421 |  | 0.2095 | 2 | 0.419 |  | 7 | 0.343 | 0.642 | 2 | 1.284
| 17 | 0.847 |  | 0.634 | 2 | 1.268 |  | 9 | -0.001 | 0.171 | 2 | 0.342
| 18 | 1.833 | RB | 1.34 | 1 | 1.34 |  | 9.8985 | -0.6 | -0.3005 | 0.8985 | -0.27
| 23 | 1.84 |  | 1.8365 | 5 | 9.1825 |  | 11.3985 | -0.6 | -0.6 | 1.5 | -0.9
| 28 | 1.847 | Garden | 1.8435 | 5 | 9.2175 |  | 12.8985 | -0.6 | -0.6 | 1.5 | -0.9
[8 empty] | 14.0985 | 0.2 | -0.2 | 1.2 | -0.24
[8 empty] | 15 | 0.421 | 0.3105 | 0.9015 | 0.27992
[8 empty] | 17 | 0.847 | 0.634 | 2 | 1.268
[8 empty] | 18 | 1.833 | 1.34 | 1 | 1.34
[8 empty] | 23 | 1.84 | 1.8365 | 5 | 9.1825
[8 empty] | 28 | 1.847 | 1.8435 | 5 | 9.2175
[5 empty] | 28 | 32.045 |  |  |  |  | 28 | 29.8049
[7 empty] | Net Area : |  | 32.045 | - | 29.8049 | 2.2401
[5 empty] | X - Section at km. |  | 1.5
| Pre-work | [5 empty] | . | Post-work | [6 empty] | 3.545
| 0 | 1.836 | Paddy land
| 5 | 1.771 |  | 1.8035 | 5 | 9.0175
| 10 | 1.82 | LB | 1.7955 | 5 | 8.9775
| 11 | 1.206 |  | 1.513 | 1 | 1.513
| 13 | 0.823 |  | 1.0145 | 2 | 2.029
| 15 | 0.43 |  | 0.6265 | 2 | 1.253
| 17 | -0.049 | CL | 0.1905 | 2 | 0.381
| 19 | 0.053 |  | 0.002 | 2 | 0.004
| 21 | 0.437 |  | 0.245 | 2 | 0.49 |  | 0 | 1.836
| 23 | 1.321 |  | 0.879 | 2 | 1.758 |  | 5 | 1.771 | 1.8035 | 5 | 9.0175
| 24 | 2.603 | RB | 1.962 | 1 | 1.962 |  | 10 | 1.82 | 1.7955 | 5 | 8.9775
| 30 | 2.611 |  | 2.607 | 6 | 15.642 |  | 11 | 1.206 | 1.513 | 1 | 1.513
| 35 | 2.616 | House Area | 2.6135 | 5 | 13.0675 |  | 13 | 0.823 | 1.0145 | 2 | 2.029
[8 empty] | 15 | 0.43 | 0.6265 | 2 | 1.253
[8 empty] | 16.545 | -0.6 | -0.085 | 1.545 | -0.13133
[8 empty] | 18.045 | -0.6 | -0.6 | 1.5 | -0.9
[8 empty] | 19.545 | -0.6 | -0.6 | 1.5 | -0.9 |  | 0.75 | -0.5
[8 empty] | 21.195 | 0.5 | -0.05 | 1.65 | -0.0825 |  | 3.25 | -0.5
[8 empty] | 21 | 0.437 | 0.4685 | -0.195 | -0.091358 |  | 5.75 | -0.5
[8 empty] | 23 | 1.321 | 0.879 | 2 | 1.758 |  | 9.8015 | 2.201
[8 empty] | 24 | 2.603 | 1.962 | 1 | 1.962
[8 empty] | 30 | 2.611 | 2.607 | 6 | 15.642
[8 empty] | 35 | 2.616 | 2.6135 | 5 | 13.0675
[5 empty] | 35 | 56.0945 |  |  |  |  | 35 | 53.1143
[7 empty] | Net Area : |  | 56.0945 | - | 53.1143 | 2.9802
[5 empty] | X - Section at km. |  | 1.6
| Pre-work | [5 empty] | . | Post-work | [6 empty] | 3.5
| 0 | 1.73 | Garden
| 5 | 1.717 |  | 1.7235 | 5 | 8.6175
| 10 | 1.706 | LB | 1.7115 | 5 | 8.5575
| 12 | 0.935 |  | 1.3205 | 2 | 2.641
| 14 | 0.417 |  | 0.676 | 2 | 1.352
| 16 | 0.031 |  | 0.224 | 2 | 0.448
| 18 | -0.07 | CL | -0.0195 | 2 | -0.039
| 20 | 0.032 |  | -0.019 | 2 | -0.038
| 22 | 0.437 |  | 0.2345 | 2 | 0.469
| 24 | 0.935 |  | 0.686 | 2 | 1.372 |  | 0 | 1.73
| 26 | 2.696 | RB | 1.8155 | 2 | 3.631 |  | 5 | 1.717 | 1.7235 | 5 | 8.6175
| 30 | 2.701 |  | 2.6985 | 4 | 10.794 |  | 10 | 1.706 | 1.7115 | 5 | 8.5575
| 35 | 2.706 |  | 2.7035 | 5 | 13.5175 |  | 12 | 0.935 | 1.3205 | 2 | 2.641
| 40 | 2.718 | Garden | 2.712 | 5 | 13.56 |  | 14 | 0.417 | 0.676 | 2 | 1.352
[8 empty] | 15.5 | 0.031 | 0.224 | 1.5 | 0.336
[8 empty] | 16.4465 | -0.6 | -0.2845 | 0.9465 | -0.26928
[8 empty] | 17.9465 | -0.6 | -0.6 | 1.5 | -0.9
[8 empty] | 19.4465 | -0.6 | -0.6 | 1.5 | -0.9
[8 empty] | 20.5715 | 0.15 | -0.225 | 1.125 | -0.25312
[8 empty] | 22 | 0.437 | 0.2935 | 1.4285 | 0.41926
[8 empty] | 24 | 0.935 | 0.686 | 2 | 1.372
[8 empty] | 26 | 2.696 | 1.8155 | 2 | 3.631
[8 empty] | 30 | 2.701 | 2.6985 | 4 | 10.794
[8 empty] | 35 | 2.706 | 2.7035 | 5 | 13.5175
[8 empty] | 40 | 2.718 | 2.712 | 5 | 13.56
[5 empty] | 40 | 64.8825 |  |  |  |  | 40 | 62.4754
[7 empty] | Net Area : |  | 64.8825 | - | 62.4754 | 2.4071
[5 empty] | X - Section at km. |  | 1.7
| Pre-work | [5 empty] | . | Post-work | [6 empty] | 0
| 0 | 2.703 | House
| 4 | 2.694 | LB | 2.6985 | 4 | 10.794
| 5 | 1.604 |  | 2.149 | 1 | 2.149 |  | 0 | 2.703
| 6 | 0.912 |  | 1.258 | 1 | 1.258 |  | 2.75 | 2.694 | 2.6985 | 2.75 | 7.4209
| 7 | 0.367 |  | 0.6395 | 1 | 0.6395 |  | 7.691 | -0.6 | 1.047 | 4.941 | 5.1732
| 9 | 0.263 | CL | 0.315 | 2 | 0.63 |  | 9.191 | -0.6 | -0.6 | 1.5 | -0.9
| 11 | 0.365 |  | 0.314 | 2 | 0.628 |  | 10.691 | -0.6 | -0.6 | 1.5 | -0.9
| 12 | 0.879 |  | 0.622 | 1 | 0.622 |  | 15.5705 | 2.653 | 1.0265 | 4.8795 | 5.0088
| 13 | 1.663 |  | 1.271 | 1 | 1.271 |  | 20 | 2.658 | 2.6555 | 4.4295 | 11.7625
| 14 | 2.653 | RB | 2.158 | 1 | 2.158 |  | 25 | 2.663 | 2.6605 | 5 | 13.3025
| 20 | 2.658 |  | 2.6555 | 6 | 15.933
| 25 | 2.663 | Garden | 2.6605 | 5 | 13.3025
[5 empty] | 25 | 49.385 |  |  |  |  | 25 | 40.8679
[7 empty] | Net Area : |  | 49.385 | - | 40.8679 | 8.5171
[5 empty] | X - Section at km. |  | 1.75
| Pre-work | [5 empty] | . | Post-work | [6 empty] | 3
| 0 | 2.692 | Play ground
| 5 | 2.683 |  | 2.6875 | 5 | 13.4375
| 10 | 2.678 | LB | 2.6805 | 5 | 13.4025
| 12 | 2.107 |  | 2.3925 | 2 | 4.785
| 14 | 1.562 |  | 1.8345 | 2 | 3.669 |  | 0 | 2.692
| 16 | 1.109 |  | 1.3355 | 2 | 2.671 |  | 5 | 2.683 | 2.6875 | 5 | 13.4375
| 18 | 0.567 |  | 0.838 | 2 | 1.676 |  | 10 | 2.678 | 2.6805 | 5 | 13.4025
| 20 | 0.179 |  | 0.373 | 2 | 0.746 |  | 12 | 2.107 | 2.3925 | 2 | 4.785
| 22 | 0.082 | CL | 0.1305 | 2 | 0.261 |  | 14 | 1.562 | 1.8345 | 2 | 3.669
| 24 | 0.185 |  | 0.1335 | 2 | 0.267 |  | 16 | 1.109 | 1.3355 | 2 | 2.671
| 26 | 0.409 |  | 0.297 | 2 | 0.594 |  | 18 | 0.567 | 0.838 | 2 | 1.676
| 28 | 0.698 |  | 0.5535 | 2 | 1.107 |  | 20 | 0.179 | 0.373 | 2 | 0.746
| 30 | 1.009 |  | 0.8535 | 2 | 1.707 |  | 21.1685 | -0.6 | -0.2105 | 1.1685 | -0.24597
| 32 | 1.408 |  | 1.2085 | 2 | 2.417 |  | 22.6685 | -0.6 | -0.6 | 1.5 | -0.9
| 34 | 1.912 | RB | 1.66 | 2 | 3.32 |  | 24.1685 | -0.6 | -0.6 | 1.5 | -0.9
| 40 | 1.919 |  | 1.9155 | 6 | 11.493 |  | 25.5935 | 0.35 | -0.125 | 1.425 | -0.17813
| 45 | 1.928 | Khal bank | 1.9235 | 5 | 9.6175 |  | 26 | 0.409 | 0.3795 | 0.4065 | 0.15427
[8 empty] | 28 | 0.698 | 0.5535 | 2 | 1.107
[8 empty] | 30 | 1.009 | 0.8535 | 2 | 1.707
[8 empty] | 32 | 1.408 | 1.2085 | 2 | 2.417
[8 empty] | 34 | 1.912 | 1.66 | 2 | 3.32
[8 empty] | 40 | 1.919 | 1.9155 | 6 | 11.493
[8 empty] | 45 | 1.928 | 1.9235 | 5 | 9.6175
[5 empty] | 45 | 71.1705 |  |  |  |  | 45 | 67.9787
[7 empty] | Net Area : |  | 71.1705 | - | 67.9787 | 3.1918
Abstract For Earth Calculation of Gunapara Khal
| C/S No |  |  | Dist. (km) | Net Area | Dist.(m) | Avg. Net Area | Volume
| 1 |  |  | 0 | 2.6344 | 0
| 2 |  |  | 0.1 | 11.8422 | 100 | 7.2383 | 723.8338
| 3 |  |  | 0.2 | 17.2226 | 100 | 14.5324 | 1453.2405
| 4 |  |  | 0.3 | 13.0462 | 100 | 15.1344 | 1513.4385
| 5 |  |  | 0.355 | 8.364 | 55 | 10.7051 | 588.7799
| 6 |  |  | 0.36 | 14.2852 | 5 | 11.3246 | 56.623
| 7 |  |  | 0.4 | 23.3057 | 40 | 18.7954 | 751.8173
| 8 |  |  | 0.5 | 13.1095 | 100 | 18.2076 | 1820.7587
| 9 |  |  | 0.575 | 14.8291 | 75 | 13.9693 | 1047.6989
| 10 |  |  | 0.58 | 13.9957 | 5 | 14.4124 | 72.0621
| 11 |  |  | 0.6 | 11.3656 | 20 | 12.6807 | 253.6131
| 12 |  |  | 0.7 | 5.3554 | 100 | 8.3605 | 836.049
| 13 |  |  | 0.8 | 15.6579 | 100 | 10.5067 | 1050.6659
| 14 |  |  | 0.9 | 8.9272 | 100 | 12.2926 | 1229.2589
| 15 |  |  | 1 | 14.6083 | 100 | 11.7678 | 1176.7797
| 16 |  |  | 1.028 | 12.608 | 28 | 13.6082 | 381.0287
| 17 |  |  | 1.043 | 9.6399 | 15 | 11.1239 | 166.8592
| 18 |  |  | 1.1 | 7.3778 | 57 | 8.5089 | 485.0049
| 19 |  |  | 1.2 | 4.9587 | 100 | 6.1683 | 616.8273
| 20 |  |  | 1.3 | 3.5059 | 100 | 4.2323 | 423.23
| 21 |  |  | 1.4 | 2.2401 | 100 | 2.873 | 287.2971
| 22 |  |  | 1.5 | 2.9802 | 100 | 2.6101 | 261.0133
| 23 |  |  | 1.6 | 2.4071 | 100 | 2.6937 | 269.3661
| 24 |  |  | 1.7 | 8.5171 | 100 | 5.4621 | 546.2097
| 25 |  |  | 1.75 | 3.1918 | 50 | 5.8544 | 292.722
[5 empty] | Total | 1750 | Total | 16304.1778

## Package_Info
Data Name | Value
Package Name | SW_HMP_01
Data Matrix | V

## Data_index
XsectionNo | chainage | r1 | r2 | c1 | c2 | KhalName | GL | Ivert Level | Retention | Required_Area | Direction
GNK0 | 0 | 6 | 20 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1
GNK1 | 100 | 37 | 51 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1
GNK2 | 200 | 68 | 84 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1
GNK3 | 300 | 98 | 110 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1
GNK4 | 355 | 125 | 137 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1
GNK5 | 360 | 151 | 163 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1
GNK6 | 400 | 177 | 189 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1
GNK7 | 500 | 203 | 215 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1
GNK8 | 575 | 231 | 245 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1
GNK9 | 580 | 257 | 271 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1
GNK10 | 600 | 284 | 298 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1
GNK11 | 700 | 311 | 325 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1
GNK12 | 800 | 341 | 353 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1
GNK13 | 900 | 367 | 378 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1
GNK14 | 1000 | 394 | 404 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1
GNK15 | 1028 | 420 | 431 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1
GNK16 | 1043 | 449 | 460 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1
GNK17 | 1100 | 478 | 490 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1
GNK18 | 1200 | 507 | 519 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1
GNK19 | 1300 | 537 | 549 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1
GNK20 | 1400 | 567 | 578 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1
GNK21 | 1500 | 597 | 609 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1
GNK22 | 1600 | 627 | 640 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1
GNK23 | 1700 | 663 | 674 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1
GNK24 | 1750 | 693 | 709 | B | D | Gunapara khal | 1.6 | -0.388 | 0.6 | 30 | 1

## Khal_Info
KhalName | Ouftfall | B | m | long_slope | Khal_Code_Name | DrawingNo | Date
Gunapara khal | -0.49 | 3 | 2 | 5 | GBK | DC5-0000 | 29/11/2024

## Notes_DC8
Sl | Notes
Adminstrative Notes | :
1 | ALL MATERIALS AND WORK MUST CONFIRM WITH TECHNICAL SPECIFICATION OF BWDB.
2 | WORK SHALL BE EXECUTED WITH PRIOR ADMINISTRATIVE AND FINANCIAL APPROVAL AND WITHIN DPP/ BUDGET PROVISION.
3 | FOR ANY ERROR, OMISSION FIELD OFFICE IS HIGHLY RECOMMENDED TO INFORM IT TO CONCERN DESIGN CIRCLE OF BWDB.
4 | NECESSARY LAND SHALL BE ARRANGED FOR EXCAVATION WORK.
Technical Notes | :
1 | ALL DIMENSIONS ARE METERE & ALL ELEVATIONS ARE IN METRE (PWD) UNLESS OTHERWISE MENTIONED IN THE DRAWING.
2 | RE-EXCAVATION WORK SHALL BE STARTED FROM D/S OF CHANNEL.
3 | TYPICAL DESIGN SECTIONS ARE PROVIDED IN THIS DESIGN FOR RE-EXCAVATION. X-SECTIONS AT AN INTERVAL NOT MORE THAN 150.00m TO BE TAKEN BY THE FIELD OFFICE FOR THE ESTIMATION OF ACTUAL VOLUME OF EARTH CUTTING.
4 | EXCAVATED EARTH SHALL NOT BE DEPOSITED WITHIN THE EXISTING SECTION OF THE RIVER / KHAL. EXCAVATED EARTH SHALL BE DEPOSITED AT A DISTANCE OF AT LEAST 3.00 METER AWAY FROM THE BANK LINE OF THE RIVER / KHAL (IN A DISCONTINUOUS MANNER TO PROVIDE SPACE FOR OVERLAND FLOW TOWARDS KHAL) FROM WHERE NO FLOW BACK OF THE EXCAVATED EARTH IN THE RIVER IS POSSIBLE. UNDER NO CIRCUMSTANCES FLOW BACK OF THE EXCAVATED EARTH INTO THE RIVER SHALL BE ALLOWED. DIPOSITION OF EARTH NOT BE MORE THAN 30M OF CONTINUOUS LENGTH AND MINIMUM 5M INTERVAL TO BE PROVIDED.
5 | EXCAVATED EARTH MAY BE USED FOR CONSTRUCTION / RE-SECTIONING OF DYKE / ROAD/ EMBANKMENT (WHERE APPLICABLE). EXCAVATED EARTH MAY BE ALSO USED FOR FILLING OF DITCH, POND, LOW LAND ETC.
6 | EXCAVATED EARTH SHALL NOT BE DIPOSITED ON ANY OPEN CHANNEL AND AT THE FLOOD PLANE OF RIVER.
7 | DIPOSITED EARTH TO BE DRESSED IN A REGULAR SHAPE & CLOSED TURFING WITH PLANTATION TO BE PROVIDED OVER DIPOSITED EARTH. PLANTATION OF VETIVER (BINNA GRASS) MAY BE PROVIDED ON SLOPE OF DIPOSITED EARTH.
8 | NO FILLING SHALL BE DONE WHERE THE EXISTING BED LEVEL OF KHAL IS LOWER THAN THE DESIGN BED LEVEL (IF EXIST).
9 | A SMOOTH TRANSITION (1:100) SHOULD BE PROVIDED BETWEEN TWO DIFFERENT BED WIDTH AND BED LEVEL AND ALSO AT THE OUTTER END OF EXISTING CULVERT/BRIDGE (IF REQUIRED).
10 | THE PROPOSED WORK SHALL BE EXECUTED PREFERABLY IN DRY SEASON.
11 | EXCAVATION MUST BE DONE VERY CAREFULLY SO THAT BASE SLAB/ FOUNDATION OF THE EXISTING REGULATOR/CULVERT/BRIDGE ETC (IF ANY) DO NOT BE DISTURBED .
12 | IF THERE EXISTS ANY STRUCTURE OTHER THAN BRIDGE WITHIN THE PROPOSED LENGTH OF THE RIVER, RE-EXCAVATION WORK IS PROHIBITED THROUGHOUT THE LENGTH OF THAT STRUCTURE.
13 | DESIGN BED LEVEL SHALL NOT BE BELOW THE FOUNDATION TOP LEVEL OF THE EXISTING STRUCTURES (IF ANY) IN THE RIVER. IF THE DESIGN BED LEVEL IS BELOW THE FOUNDATION TOP LEVEL THEN THE DIFFERENCE BETWEEN THESE LEVELS SHALL BE MATCHED IN A SLOPE 1:100, OR AT A DISTANCE OF 100 M, WHICHEVER IS HEIGHER (U/S AND D/S OF THE STRUCTURE) AS SHOWN IN THE DRAWING.
14 | RE-EXCAVATION OF KHAL/ RIVER WILL FACILITATE QUICK DRAINAGE, FLUSHING & STORAGE OF WATER. BUT COMPLETE DRAIN OUT OF BEEL AREA SHALL NOT BE ALLOWED FOR MAINTAINING ECOLOGICAL BALANCE.
15 | IF THE BED LEVEL OF OUTFALL KHAL/RIVR IS HIGHER THAN THE DESIGN BED LEVEL OF PROPOSED KHAL, THEN RE-EXCAVATION OF PROPOSED KHAL TO BE IMPLEMENTED AFTER IMPLEMENTATION OF RE-EXCAVATION OF OUTFALL KHAL/RIVER.
16 | RE-EXCAVATION OF KHAL SHALL BE STARTED FROM D/S.
17 | THIS DRAWING HAS BEEN PREPARED AS PER PROPOSAL SUBMITTED BY SE, KHULNA O & M CIRCLE, BWDB, KHULNA VIDE HIS OFFICE MEMO NO-8/2, DATE: 02/02/2022

## Headers
Data | Values
Organization | Bangladesh Water Development Board
Design_Office | Office of The Superintending Engineer,Design Circle-5
Project Name | CRISP-WRM
Work_Name | Re-excavation of Gunapara Khal from km. 0.000 to km. 1.750 in polder -1 in c/w Tarail-Pachuria Sub-Project under CRISP-WRM under Specialized Division. BWDB, Gopalganj during the year 2024-2025
Designed_by | (Md. Mostafa Kamal),AE
Recommended_by | (MD. Kamrul Hasan),EE
Approved_by | (Jakaria Pervez),SE
Clinet_Division | SMO, IDWRM-KT
Design_Month | December,2024

## Notes
Sl | Notes
Adminstrative Notes | :
1 | FOR ANY ERROR, OMISSION OR CONFUSION PLEASE REFER TO THIS OFFICE AS QUICK AS POSSIBLE FOR FURTHER NECESSARY ACTION
2 | WORK SHALL BE EXECUTED AFTER ADMINISTRATIVE AND FINANCIAL APPROVAL AND TECHNICAL SANCTION FROM THE COMPETENT AUTHORITY AND WITHIN THE DPP / BUDGET PROVISION.
3 | ALL DIMENSIONS AND ELEVATIONS ARE IN MILLIMETER AND METER(PWD) RESPECTIVELY UNLESS OTHERWISE MENTIONED IN THE DRAWING.
4 | ALL MATERIALS AND WORK MUST CONFIRM WITH BWDB TECHNICAL SPECIFICATION.
5 | NECESSARY LAND (IF REQUIRED) SHALL BE ARRANGED BY THE FIELD OFFICE FOR RE-EXCAVATION & CONSTRUCTION OF DYKE (IF REQUIRED).
6 | THE RE-EXCAVATION OF THE KHAL SHALL START FROM DOWNSTREAM SIDE.
7 | A SMOOTH TRANSITION SHALL BE PROVIDED BETWEEN THE EXCAVATED SECTION OF THE KHAL AND THE EXISTING SECTION.
8 | A SMOOTH TRANSITION 1:100 SHALL BE PROVIDED AT THE POINT WHERE DESIGN BED WIDTH OR BED LEVEL CHANGES. | z
9 | A SMOOTH TRANSITION AT A SLOPE OF 1:100 SHALL BE KEPT BETWEEN APRON LEVEL OF CONNECTING STRUCTURE (IF ANY) TO DESIGN BED LEVEL OF KHAL.
10 | THE RE-EXCAVATION WORK SHALL BE DONE IN THE DRY SEASON WHEN WATER LEVEL IS AT OR NEAR LOW WATER LEVEL
11 | NO FILLING SHALL BE DONE WHERE THE EXISTING BED LEVEL OF THE KHAL IS LOWER THAN THE DESIGN BED LEVEL AND EXISTING SIDE SLOPE IS FLATTER THAN DESIGN SECTION.
12 | ANY OUTFALL/OFFTAKE RIVER/KHAL WHICH IS CONNECTED WITH THE PROPOSED KHAL SHALL BE KEPT OPEN.
13 | MANAGEMENT OF EXCAVATED EARTH:
a) HEAP OF EXCAVATED EARTH ON BANK SHALL BE AVOIDED. EXCAVATED EARTH TO BE SPREAD OVER THE BANKS FOR THE PREPARATION OF WALKWAY OR SPREAD OVER THE BANK AT LEAST 10.00M AWAY FROM THE BANK LINE OF THE KHAL OR TO A SAFE DISTANCE FROM WHERE NO DEPOSITED EARTH SHALL BACK FLOW INTO THE KHAL. FLOWING BACK OF DEPOSITED EARTH INTO THE KHAL SHALL NOT BE ALLOWED.
b) EXCAVATED EARTH MAY BE USED FOR CONSTRUCTION / RE-SECTIONING OF INTERNAL DYKE / ROAD / EMBANKMENT / LAND DEVELOPMENT / DITCH FILLING WITHIN THE EXCAVATION COST AS PER SCHEDULE ITEM (WHERE APLLICABLE).
c) TO AVOID THE WATER LOGGING IN ADJACENT AREA, DRAINAGE STRUCTURE MAY BE PROVIDED ALONG THE BANK / NEAR OUTFALL OF THE RIVER / KHAL (IF REQUIRED).
d) FINE DRESSING WITH TURFING ON DYKE SHALL BE DONE.
14 | TYPICAL DESIGN SECTIONS ARE PROVIDED IN THIS DESIGN FOR RE-EXCAVATION. CROSS SECTIONS AT AN INTERVAL NOT MORE THAN 150.00M TO BE TAKEN BY THE FIELD OFFICE FOR THE ESTIMATION OF ACTUAL VOLUME OF EARTH CUTTING. EXCAVATED EARTH TO BE COLLECTED FROM RIVER CAREFULLY CONSIDERING NO ADVERSE EFFECT ON CHANNEL FLOW AND BANK ERROSION. ANY PROPOSED BOX CULVERT /BRIDGE OVER THIS KHAL WILL BE DESIGNED CONSIDERING DESIGN SECTIONS OF THIS KHAL.IF THE BED LEVEL OF OUTFALL KHAL/RIVR IS HIGHER THAN THE DESIGN BED LEVEL OF PROPOSED KHAL, THEN RE-EXCAVATION OF PROPOSED KHAL TO BE IMPLEMENTED AFTER IMPLEMENTATION OF RE-EXCAVATION OF OUTFALL KHAL/RIVER.
15 | EXCAVATED EARTH TO BE COLLECTED FROM RIVER CAREFULLY CONSIDERING NO ADVERSE EFFECT ON CHANNEL FLOW AND BANK ERROSION.
16 | ANY PROPOSED BOX CULVERT /BRIDGE OVER THIS KHAL WILL BE DESIGNED CONSIDERING DESIGN SECTIONS OF THIS KHAL
SPECIAL NOTES: | :
1 | THIS REVISED DRAWING HAS BEEN PREPARED AS PER PROPOSAL AND DESIGN DATA SUBMITTED BY SE, KUSHTIA O & M CIRCLE, BWDB, KUSHTIA VIDE HIS OFFICE MEMO NO-3M-1/1358 DATE: 07/02/2023.
2 | THIS RE-REEXCAVATION WORK HAS ALSO BEEN DESIGNED CONSIDERING THE WATER RESERVOIR AS WELL AS FOR IRRIGATION PURPOSE.
3 | IF THE EXISTING BED LEVEL OF THE OUTFALL (RIVER / KHAL) IS HIGHER THAN DESIGN BED LEVEL OF THIS KHAL, RE-EXCAVATION OF THIS KHAL MUST BE DONE IN PARALLEL/ AFTER THE RE-EXCAVATION OF ITS OUTFALL RIVER / KHAL AS PER APPROVED DESIGN.
4 | IF THERE EXISTS ANY STRUCTURE ( REGULATOR, BOX CULVERT ETC.) OTHER THAN BRIDGE WITHIN THE PROPOSED LENGTH OF THE KHAL, RE-EXCAVATION WORK IS PROHIBITED THROGHOUT THE LENGTH OF THAT STRUCTURE.
5 | DESIGN BED LEVEL OF THE KHAL SHALL NOT BE BELOW THE FOUNDATION TOP LEVEL OF THE EXISTING STRUCTURES (IF ANY) IN THE KHAL. IF THE DESIGN BED LEVEL IS BELOW THE FOUNDATION TOP LEVEL THEN THE DIFFERENCE BETWEEN THESE LEVELS SHALL BE MATCHED IN A SLOPE 1:100, OR A DISTANCE OF 100 M, WHICHEVER IS HEIGHER (U/S AND D/S OF THE STRUCTURE), (OR AS SHOWN IN THE DRAWING).
6 | DESIGN BED LEVEL & BED WIDTH OF THIS KHAL HAVE BEEN FIXED CONSIDERING THE BED LEVEL & BED WIDTH OF EXISTING KHAL/ FLOOR LEVEL OF EXISTING HYDRAULIC STRUCTURE.